VERSE FOR YOU

Product Decision Log

Check-In #2  ·  April 18, 2026

This document records key product decisions made during the week of April 11–18, 2026. Each entry captures what was decided, the rationale, alternatives considered, and expected impact. Decisions are preserved here as the source of truth for scope and strategy choices.

Owner: Pedro Siqueira    |  Prepared by: Claude    |  Period: April 11–18, 2026

# Decision #1 — Freemium Limits Added

Summary

The app now limits free users to 5 verse searches per day. Users who exceed the limit are prompted to upgrade to Premium ($4.99/mo or $39.99/yr). Existing beta users and the donation flow are unaffected.

Decision Details

| Date decided | April 14, 2026 |
| --- | --- |
| Status | Implemented — live in TestFlight beta |
| Decision maker | Pedro Siqueira |
| Category | Monetization |

Rationale

Three factors drove this decision:

- Conversion mechanics: The freemium model needs a friction point that creates upgrade motivation. With unlimited free usage, there is no push toward Premium. A daily cap of 5 creates gentle pressure without alienating casual users.

- Market precedent: YouVersion, Hallow, and Glorify all use engagement-gated models. Users in the faith app category are accustomed to soft limits.

- Revenue sustainability: Donations alone are unlikely to sustain ongoing development. The freemium limit is the primary conversion lever for the subscription tier.

Alternatives Considered

| Unlimited free (ads) | Rejected — ad model conflicts with the pastoral, distraction-free brand |
| --- | --- |
| Hard paywall | Rejected — too high a barrier; kills organic word-of-mouth |
| 10 searches/day | Considered — chose 5 as a firmer but still generous limit |
| Feature gating only | Deferred — may gate advanced features in v1.1 in addition |

Expected Impact

- Conversion rate target: 4% of active free users to Premium within 30 days of hitting the cap.

- Free users under the cap are unaffected and continue to evangelize the app.

- Risk: If the cap feels too restrictive, we will raise it to 10 in v1.1 based on TestFlight feedback.

Follow-up Actions

- Monitor TestFlight beta feedback on the cap — collect qualitative reactions from testers.

- Implement upgrade prompt UI with a clear value prop when the cap is reached.

- Set up analytics event: cap_reached to measure daily conversion to upgrade flow.

# Decision #2 — Reading Plans Cut from v1 Scope

Summary

The ReadingPlanScreen feature has been removed from the v1 launch scope. It will ship in v1.1 shortly after the initial App Store launch, with a full multi-plan experience (7-day, 21-day, seasonal).

Decision Details

| Date decided | April 15, 2026 |
| --- | --- |
| Status | Deferred — screen code retained but removed from navigation |
| Decision maker | Pedro Siqueira |
| Category | Scope |

Rationale

- Build quality risk: ReadingPlanScreen is 664 lines but represents a single-plan view. The category standard is multiple plans with per-user progress tracking, which requires significant additional backend work.

- Timeline pressure: Insufficient runway to build Reading Plans to a quality standard before the App Store submission target of April 25.

- Core loop completeness: The emotion → verse → journal loop is strong and complete. Reading Plans are an enhancement, not a foundation.

- First-impression risk: A half-built Reading Plans tab at launch would hurt App Store reviews more than its absence.

Alternatives Considered

| Ship with 1 plan (7-day anxiety) | Rejected — single plan feels thin; sets wrong expectation |
| --- | --- |
| Hide tab, ship in background | Rejected — users may find hidden routes; cleaner to remove from nav |
| Defer progress tracking only | Rejected — too hard to retrofit once the screen ships without it |
| Defer to v1.1 (chosen) | Accepted — clean scope, faster launch, full feature ships properly |

Expected Impact

- v1 ships with a complete and polished 4-screen experience: Home, Search, Journal, Settings.

- Reading Plans in v1.1 may generate a second wave of App Store visibility as a featured update.

- Risk: Some reviewers may note the absence. Manageable given the strength of the core loop.

Follow-up Actions

- Retain ReadingPlanScreen.tsx as the foundation for v1.1 Reading Plans.

- Add a Coming Soon teaser card on Home screen to set expectation and build anticipation.

- Design the full multi-plan experience for the v1.1 sprint.

# Decision #3 — Launch Date Pushed to Late May

Summary

The original public launch target of May 9, 2026 has been moved to late May 2026 (targeting the week of May 25). The App Store submission target of April 25 remains in place. The extra time is used for TestFlight feedback incorporation and final polish.

Decision Details

| Date decided | April 18, 2026 (Check-In #2) |
| --- | --- |
| Status | Confirmed — timeline updated in all planning documents |
| Decision maker | Pedro Siqueira |
| Category | Timeline |
| Previous target | May 9, 2026 |
| New target | Late May 2026 (week of May 25) |

Rationale

- TestFlight feedback loop: With beta testers now onboarded, the feedback window needs time to yield actionable signal. A May 9 launch would allow only ~2 weeks of feedback before submission.

- App Store review buffer: Apple review can take 24–48 hours, but rejections can add a week or more. A late May launch allows a rejection-and-resubmit cycle without missing the window.

- Polish quality: The April 16 daily review surfaced P1/P2 polish items (typography, dark mode contrast, share cards, error states). Extra weeks allow these to land before launch.

- Revenue projection unchanged: Late May launch shifts ~3 weeks of projected revenue later but does not affect the Year 1 peak estimate.

Revised Timeline

| Apr 18–25 | App Store submission prep (screenshots, copy, privacy policy, App Store Connect) |
| --- | --- |
| Apr 25–28 | Submit to App Store for review |
| Apr 28 – May 9 | Apple review + any required fixes / resubmission |
| May 9–25 | TestFlight feedback iteration + final polish sprint |
| Late May 2026 | Public App Store launch + marketing push |

Expected Impact

- Higher first-impression quality: A polished launch drives stronger initial App Store reviews, which have outsized impact on organic discovery.

- Reduced launch-day hotfix risk: More testing time means fewer P0 bugs surfacing in public reviews.

- Revenue delay: Approximately 2–3 weeks of projected revenue shifted later. Acceptable given the quality tradeoff.

Follow-up Actions

- Finalize App Store submission checklist by April 19.

- Assign P1/P2 polish items from the April 16 daily review to the May 9–25 sprint.

- Update all external communications to reflect the late May launch.

## Summary of This Week’s Decisions

| # | Decision | Category | Status |
| --- | --- | --- | --- |
| 1 | Freemium limits (5/day free) | Monetization | Implemented |
| 2 | Reading Plans cut from v1 | Scope | Deferred to v1.1 |
| 3 | Launch pushed to late May | Timeline | Confirmed |

Next check-in: April 25, 2026 — App Store submission status + beta feedback summary.