## Slide 1
WEEKLY CHECK-IN · APRIL 18, 2026
Verse for You
CHECK-IN #2
Auth Live · TestFlight Beta · App Store Next
Prepared by Claude · Verse for You Build Session

## Slide 2
APP STATUS
Verse for You · Check-In #2 · April 18, 2026
Where We Stand
As of April 18, 2026 — Check-In #2
95%
Complete
Up from 85%
4
Screens Built
Home · Search · Journal · Settings
Live
TestFlight Beta
Beta testers onboarded
Auth
Apple & Google
Cloud sync active
SHIPPED THIS WEEK
Sign in with Apple & Google (auth fully wired)
Cloud journal sync — verses survive reinstalls
TestFlight beta submitted & live with testers
UI polish: animations, typography, spacing
Bug fixes + HomeScreen & routes.ts refactored

## Slide 3
KEY DECISIONS
Verse for You · Check-In #2 · April 18, 2026
Three Big Calls This Week
Decisions that shape the path to launch
01
MONETIZATION
Freemium Limits Added
Free users now get 5 verse searches per day. Premium removes all limits. Lower barrier to first install while creating a clear upgrade trigger.
02
SCOPE
Reading Plans Cut from v1
ReadingPlanScreen is removed from the launch scope. Complex to build well and risks delaying the App Store submission. Will ship in v1.1.
03
TIMELINE
Launch Pushed to Late May
Originally targeting May 9. Extra time allows for proper beta feedback collection and a polished App Store submission. Quality over speed.

## Slide 4
MONETIZATION MODEL
Verse for You · Check-In #2 · April 18, 2026
How Verse for You Makes Money
Updated freemium model — lower barrier, clearer upgrade path
FREE
$0
· 5 verse searches/day
· Verse of the Day
· Basic journal (local)
· 3 Bible translations
· Donation option
Great for casual users
PREMIUM
$4.99/mo
· Unlimited verse searches
· Cloud journal sync
· All 9 translations
· Offline mode
· Ad-free forever
Primary revenue driver
DONATIONS
One-time
· $5 · $10 · $25 · $50
· Stripe Checkout (live)
· No account required
· Community goodwill
· Strong at launch
Already built & live

## Slide 5
LAUNCH TIMELINE
Verse for You · Check-In #2 · April 18, 2026
Road to Late May Launch
Updated from May 9 — extra polish before public launch
Apr 11
Check-In #1
Security review · 85% complete
Apr 11–18
Polish Sprint
Auth · UI · TestFlight · Refactors
Apr 18
Check-In #2
TestFlight live · Auth done · 95% complete
TODAY
Apr 18–25
App Store Prep
Screenshots · Description · Keywords · Privacy policy
Apr 25–28
Submit to App Store
Apple review (typically 24–48 hrs)
May 2–9
Beta Feedback Loop
TestFlight fixes · Final polish based on feedback
Late May
Public Launch
App Store live · Marketing push begins

## Slide 6
NEXT WEEK
Verse for You · Check-In #2 · April 18, 2026
App Store Submission Week
April 18–25 · Everything needed to submit to Apple
01
App Store Screenshots
6.5" iPhone + 12.9" iPad screenshots for all 5 key screens. Use the simulator to capture clean, representative shots.
02
App Description & Keywords
Write the 170-char short description and 4,000-char full description. Research keywords: 'Bible verse anxiety', 'daily devotional', 'Christian app'.
03
Privacy Policy
Create a simple privacy policy page (required by Apple). Covers data collection, OpenAI usage, Stripe, and analytics.
04
App Store Connect Setup
Create the app listing, upload metadata, set pricing (Free + In-App Purchase for Premium), configure TestFlight external testing.
05
Submit for Review
Target submission by Apr 25. Apple review typically 24–48 hours. Prepares for late May launch window.

## Slide 7
REVENUE PROJECTION
Verse for You · Check-In #2 · April 18, 2026
Conservative · 12 Months Post-Launch
Updated for late May launch — same assumptions, 3 weeks later start
KEY ASSUMPTIONS
Launch date
Late May 2026
Free users (mo 1)
500
Paid conversion
4%
Sub price
$4.99/mo
Freemium cap
5 searches/day
Church licenses
2 by mo 6
Donations avg
$12
Growth rate
~25%/mo
Year 1 peak
~$7,800/mo
Chart: 
| Mo 1 | Mo 2 | Mo 3 | Mo 4 | Mo 5 | Mo 6 | Mo 7 | Mo 8 | Mo 9 | Mo 10 | Mo 11 | Mo 12
Monthly Revenue | 100 | 200 | 420 | 700 | 1100 | 1650 | 2400 | 3400 | 4600 | 5800 | 6900 | 7800

## Slide 8
WHAT'S NEXT
App Store by
Late May
01
App Store submission prep this week
02
TestFlight feedback → final polish
03
Marketing assets & ASO ready by launch
Verse for You · Check-In #2 · April 18, 2026 · Prepared by Claude